## DeliveryHealth
Dimension | RAG | Trend | Evidence | Owner | Planned Action | Target Date
Scope | Green | Stable | No scope creep | Sunil | Monitor weekly | -
Schedule | Amber | Worsening | Data migration delays | Ravi | Weekend batch | 2026‑06‑28
Cost | Green | Stable | Within budget | PMO | No action | -
Quality | Amber | Stable | UAT defects increasing | QA Lead | Add regression suite | 2026‑06‑25
Resources | Red | Worsening | 2 consultants resigned | HR | Backfill + contractors | 2026‑07‑05
Client Satisfaction | Green | Improving | Positive feedback | Sunil | Maintain cadence | -