## Raid
ID | Type | Title | Description | Category | Probability | Impact | Score | Owner | Mitigation | Target Date | Status | Client Visible | Comments
R‑001 | Risk | Data Migration Delay | Legacy extracts failing intermittently | Schedule | 4 | 5 | 20 | Ravi | Add retry logic + increase extraction window | 2026‑07‑15 | Open | Yes | High impact on SIT
R‑002 | Risk | Integration Bottleneck | Middleware queue spikes during peak hours | Tech | 3 | 4 | 12 | Priya | Scale queue + add async processing | 2026‑07‑10 | In Progress | No | Monitoring enabled
I‑003 | Issue | Defect Leakage | Sev‑1 defects found in UAT | Quality | - | - | - | Sunil | Add regression suite + RCA | 2026‑06‑30 | Open | Yes | Client escalated
A‑004 | Assumption | Client Data Freeze | Client will freeze data by 2026‑06‑25 | Scope | - | - | - | PMO | Confirm freeze date weekly | 2026‑06‑25 | Open | Yes | Pending confirmation
D‑005 | Dependency | Infra Provisioning | Awaiting cloud infra from client | Vendor | - | - | - | Client | Weekly follow‑up | 2026‑06‑22 | Open | Yes | Blocking SIT